## Overview
AI Adoption and Workforce Planning — Requirements Workbook
Version 1.0 · November 2026 · Stakeholder is hypothetical; data is public (Anthropic Economic Index, CC-BY 4.0).
How to use
• Each sheet is one BA artefact: Stakeholders, Requirements, User Stories, KPI Definitions, Assumptions, Traceability.
• Yellow cells on Traceability (Result) are yours to update: set Pass or Fail after checking each item in Power BI.
• Dropdowns keep priority, status and result values consistent.
• The summary below updates automatically from the other sheets.
Summary
Must requirements | 7
Should requirements | 2
Could requirements | 1
Won't (out of scope) | 2
Traceability checks passed | 0
Traceability checks failed | 0
Traceability checks not tested | 10
Unvalidated assumptions | 4

## Stakeholders
Stakeholder | Role in the decision | Interest | Influence | Engagement approach | What they need from the project
L&D Manager | Decision owner; owns training budget | High | High | Manage closely | Ranked shortlist of 3 role–task pilots with evidence and cautions
Leadership sponsor | Approves budget and pilot | Medium | High | Keep satisfied | One-page summary: why these 3, cost of pilot, how success is measured
Team leads of shortlisted roles | Run the pilot in their team | High | Medium | Keep informed and involved | Which task changes, time needed, how output quality is checked
Employees in pilot roles | Do the work that changes | High | Low | Keep informed | Training, clear review steps, reassurance on role impact
IT / Security | Approves tool access and data handling | Medium | High | Keep satisfied | Which AI tool, what data enters it, access controls
Data Analyst (project author) | Builds evidence and dashboard | High | Low | — | Clear questions, agreed metrics, acceptance checks

## Requirements
ID | Type | Requirement | Priority (MoSCoW) | Question | Source
BR-01 | Business | The L&D manager can identify three role–task combinations to investigate for AI training or a pilot. | Must | Q3 | Business brief §3
FR-01 | Functional | Dashboard shows the top tasks by AI usage share on Claude.ai. | Must | Q1 | Business brief §4
FR-02 | Functional | User can filter occupations by SOC major group and inspect the tasks linked to each occupation. | Must | Q1 | Business brief §4
FR-03 | Functional | Dashboard compares Claude.ai and API usage: usage share and automation share by occupational group. | Should | Q2 | Business brief §4
FR-04 | Functional | Pilot page shows each candidate's usage share, success rate and Core/Supplemental flag, plus the ranking rule in plain words. | Must | Q3 | Business brief §5
FR-05 | Functional | Pilot page shows the data limitations (one week, classifier-based, selection bias, privacy filter, US definitions). | Must | Q3 | Business brief §10
FR-06 | Functional | User can export the pilot shortlist table. | Could | Q3 | Assumed L&D need
NFR-01 | Non-functional | Every dashboard total reconciles with a saved SQL query. | Must | All | Business brief §9
NFR-02 | Non-functional | The pipeline reruns from the raw files with one command per step. | Should | All | Portfolio reproducibility
NFR-03 | Non-functional | Data sources and CC-BY licence are credited in the dashboard and README. | Must | All | Dataset licence
OUT-01 | Out of scope | Country-level comparisons and regressions. | Won't | — | Business brief §7
OUT-02 | Out of scope | Forecasting, predictive models and job-displacement estimates. | Won't | — | Business brief §7

## User Stories
Story ID | As a… | I want… | So that… | Acceptance criteria (Given / When / Then) | Linked requirement
US-01 | L&D manager | to see which tasks people use AI for most | I know where demand for AI support already exists | Given the AI usage overview page, when it loads, then the top 10 tasks are shown with usage share, and their total matches q1_usage_by_task.sql. | FR-01
US-02 | L&D manager | to filter by occupational group and see each occupation's tasks | I can relate the evidence to roles in my organisation | Given the Roles and tasks page, when I select a SOC major group, then only occupations in that group are listed, and the task count matches q1_usage_by_occupation.sql. | FR-02
US-03 | L&D manager | to compare consumer and business AI use | I can tell tasks people try by hand from tasks businesses already automate | Given the Roles and tasks page, when I view the platform comparison, then usage and automation share are shown for both platforms per group, matching q2_platform_comparison.sql. | FR-03
US-04 | L&D manager | a shortlist of three pilot candidates with reasons and cautions | I can propose a pilot to leadership with confidence | Given the Pilot opportunities page, when it loads, then three role–task cards show usage share, success rate, Core flag and a caution, and the ranking rule is stated. | BR-01, FR-04, FR-05

## KPI Definitions
KPI | Definition / formula | Source query (planned) | Owner | Decision it informs | Status
Usage share | Records mapped to a task ÷ all task-mapped records, per platform | q1_usage_by_task.sql | Data Analyst | Where AI demand exists | Confirmed
Collaboration mix | Share of directive, feedback loop, task iteration, learning, validation | q2_platform_comparison.sql | Data Analyst | How people work with AI on a task | Confirmed
Automation share | (Directive + feedback loop) ÷ classified records | q2_platform_comparison.sql | Data Analyst | Whether a task is already delegated to AI | Confirmed
Task success rate | Yes ÷ (yes + no) per task; not_classified excluded from the denominator | q3_pilot_candidates.sql | Data Analyst | Whether AI is reliable enough for a pilot | Confirmed
Core task flag | O*NET Task Type = Core for the occupation | q3_pilot_candidates.sql | Data Analyst | Whether the task matters to the role | Confirmed
Speedup | Human-only time ÷ human-with-AI time per task (Claude's estimates) | q3_pilot_candidates.sql | Data Analyst | How much time AI could save on a task | Confirmed

## Assumptions
ID | Assumption | Status | How a real team would validate it | Impact if wrong
A-01 | The organisation has roles similar to the shortlisted US occupations | Unvalidated | Map shortlisted occupations to internal job titles with HR | Shortlist may not apply
A-02 | A pilot can run for 6–8 weeks with one team | Unvalidated | Confirm with team lead and IT | Pilot scope must shrink
A-03 | Time per task and error rate can be measured before and after the pilot | Unvalidated | Agree a baseline measurement with the team lead | Success cannot be proven
A-04 | Classifier-judged task success is a reasonable proxy for real success | Partly checked | Anthropic reports directional accuracy; a pilot would measure real outcomes | Pilot candidates may underperform
A-05 | One week of usage (13–20 Nov 2025) is representative | Unvalidated | Compare with another AEI release in a later version | Rankings may shift over time
A-06 | Success rate = yes ÷ (yes + no); conversations not classified for success are excluded | Decided | Compare rankings with and without not_classified in the denominator | Success rates shift for tasks with many unclassified conversations
A-07 | When one task belongs to several occupations, its usage is split equally between them | Decided | Weight the split by O*NET task importance in a later version | Occupation totals shift slightly
A-08 | Major group is derived from the first two digits of the occupation code (valid for SOC 2010 and 2019); minor groups only for SOC 2019 codes | Validated | Major-group shares reproduce Anthropic's published figures | Minor-group views cover only 60% of Claude.ai usage
A-09 | none / not_classified tasks stay in usage totals but are excluded from rankings | Decided | Top-10 share reproduces Anthropic's 24% / 32% with this rule | Rankings would include non-tasks

## Traceability
Requirement ID | SQL query | Power BI page / visual | Acceptance check | Result | Priority (from Requirements)
BR-01 | q3_pilot_candidates.sql | Pilot opportunities | Three candidates shown with evidence and cautions | Not tested | Must
FR-01 | q1_usage_by_task.sql | AI usage overview | Top 10 total in Power BI = query total | Not tested | Must
FR-02 | q1_usage_by_occupation.sql | Roles and tasks | Group filter shows only that group; counts match query | Not tested | Must
FR-03 | q2_platform_comparison.sql | Roles and tasks | Platform figures match query per group | Not tested | Should
FR-04 | q3_pilot_candidates.sql | Pilot opportunities | Each card shows usage, success, Core flag; rule stated | Not tested | Must
FR-05 | — | Pilot opportunities | Limitations note visible on the page | Not tested | Must
FR-06 | — | Pilot opportunities | Shortlist table can be exported | Not tested | Could
NFR-01 | checks_reconciliation.sql | All pages | All reconciliation queries match dashboard totals | Not tested | Must
NFR-02 | src/ scripts | — | Fresh clone reproduces processed files and query outputs | Not tested | Should
NFR-03 | — | All pages + README | Anthropic EconomicIndex credited with CC-BY 4.0 | Not tested | Must